## Version History
Minutes of the Meeting Version 1.3
| Version No | Date | Prepared by | Reviewed by | Change Details
| 1.1 | 2019-04-11 | Deepak Menon | Lavanya Gatamaneni | Updating the previous actions
| 1.2 | 2019-04-12 | Deepak Menon | Lavanya Gatamaneni | Updating the pending actions
| 1.3 | 2019-04-15 | Deepak Menon | Lavanya Gatamaneni | Closing of the request

## Minutes of the Meeting
MINUTES OF MEETING Version 1.3
Project Name /Function Name |  | Blue Ally |  | Date [dd-mmm-yyyy] | 2019-04-11
Meeting Called By |  | Deepak Menon |  | Topic | Team Meeting
Schedule Time of Start |  | Actual Time of Start |  | Venue
10:30 AM EST |  | 11:00 AM EST |  | Tanvi IT Solutions Inc
Planned Duration of the Meeting |  | Actual Duration of the Meeting |  | Date/ Time/ Venue of Next Meeting
30 mins |  | 30 mins |  | 2019-04-11
Members Present |  | Ravalika Rao, Sreeraj Rao, Prashanth Prabhakaran, Lavanya Gatamaneni, Eswara Prasad Gatamaneni, Nagoor Inaganti, Deepak Menon
Members Absent
Invitees |  | Nagoor Inaganti, Eswara Prasad Gatamaneni, Lavanya Gatamaneni
Objectives of the Meeting |  | Recruitment Team meeting
Pending Action Points from Previous Meeting
S.No. | Action/ Observation | Responsibility | Projected Date of completion [dd-mmm-yyyy] | Closure status/ Date of closure [dd-mmm-yyyy] | Remarks
1 | Candidate Sourcing | Deepak Menon | 2019-04-11 | 2019-04-12 | Online Recruiting portals
2 | Shortlisting candidate for interview | Deepak Menon | 2019-04-12 | 2019-04-13 | Preliminary Interview
3 | Submission of profile to the client | Lavanya Gatamaneni | April 15 2019 | 2019-04-15 | Waiting for feedback
Gist of the Meeting
S.No. | Agenda Item |  |  | Highlights/ Observations/ Conclusions
1 | Discussed about client's business objectives, requirements in the specific technology |  |  | Requirement : DevOps Engineer Location: Texas
2 | Discussion for the pool of candidates |  |  | Identifying the potential candidate for interviewing
3 | Discussion on the visa requirements for the candidate |  |  | US Citizen, GC holders, H1B on Tanvi IT payroll.
Action Points
S.No. | Action | Responsibility | Projected Date of completion | Closure status/ Date of closure | Remarks
1 | Sourcing DevOps engineer in the Texas location | Deepak Menon | April 12 2019 | April 15 2019 | Delay in the submittal of the candidate's profile due to the location constrain.
Recorded By
Classification: TANVIIT ¦ CONFIDENTIAL/INTERNAL/PUBLIC